## Sheet1
Quarter/Year | Week | <component> | Goal | Est.Time(hrs) | Difficulty(1-5)
Q1/2026 | Week1 | GitHub Repository And Python App | Create repo,scaffold Python Flask app,add Makefile and requirements.txt | 4 | 3
Q1/2026 | Week1 | Unit Tests And Linting | Write basic test cases and run link checks | 3 | 2
Q1/2026 | Week2 | CI/CD Pipelines | Setup Github Actions CI and Azure Pipeline CD | 5 | 4
Q1/2026 | Week2 | Deployment and validation | Deploy App to Azure App Service, Test API, Capture Screenshots | 4 | 3
Q1/2026 | Week2 | ReadMe And Documentation | Complete ReadMe, add trello link, spreadsheet link and screencast. | 3 | 2